## Layered Audit
Model | Sr.No | Date | Station ID | Workstation | Auditor | NC’s | Action Plan | 4M | Responsibility | target Date | Status
THAR ROXX | S_FL_ISF_RX_Aug24_AG_40 | 2024-08-20 | FAI-04 | I shaft fitment | Ashhutossh Gondhalaykaar / Swaroop Joshi / Mukesh Deo | Non Availibility of DC tool for critical Joints 1. I-Shaft fitment 2. V clamp 3. Alternator 4. Starter motors 5. Fuse box nut | PCA 1: Pneumatic tool / battery too with line interlink with sticker mentioned "Ok". PCA 2: DC tool to be installed with actual torque value delivered mention on sticker - Budget issue (75Lac) | Machine | Kiran Kasar | TBD | R