## Sheet1
Model | Sr.No | Date | Station ID | Workstation | Auditor | NC’s | Action Plan | 4M | Responsibility | target Date | Status
THAR ROXX | S_FL_ISF_RX_Aug24_AG_40 | 2024-08-20 |  | I shaft fitment | Ashhutossh Gondhalaykaar / Swaroop Joshi / Mukesh Deo | Non Availibility of DC tool for critical Joints 1. I-Shaft fitment 2. V clamp 3. Alternator 4. Starter motors 5. Fuse box nut | PCA 1: Pneumatic tool / battery too with line interlink with sticker mentioned "Ok". PCA 2: DC tool to be installed with actual torque value delivered mention on sticker - Budget issue (75Lac) | Machine | Kiran Kasar | TBD | R
THAR ROXX | S_CH_SDPF_RX_Mar26_SJ_01 | 2026-03-02 |  | Final Line | Swaroop Joshi | ABS wire clipping not done near DP pipe downstream | Root cause: ABS wire Edge clipping not done near DP pipe downstream on LH Hydra mount by associate ICA -All WIP verified for ABS wire routine Edge clippings on the Hydra mount & Awareness given via DRF and OPL - 03-Mar-26 PCA - Confirmation Marking started on ABS wire Edge clippings - 03-Mar-26 SOS modified & updated according to SOS, OPL given to all associates | Man | Rajesh Morkar | 2026-03-04 | Y
XUV3XO | X_T1_WS_3XO_Mar26_SJ_01 | 2026-03-09 |  | Trim 1 | Swaroop joshi | promotor not used before RH Rear Waist seal | RC- associate not followed the SOS ICA - Awareness given to associate through DRF | Man | Tushar Kulkarni | 2026-03-09 | Y
THAR ROXX | S_FL_ACF_RX_Feb26_SJ_01 | 2026-02-04 |  | Final Line | Swaroop Joshi | HFM sensor protective cap removed before fitment. | Root cause: Stage associate removing caps during mass flow sensor sub-assembly and keeping air cleaner on trolly. Associate is not following process as he is doing multiple air cleaner sub assembly and keeping it on trolly. ICA - Ensured protective caps available on all air cleaners, as precaution random 2 vehicle opened for HFM internal check PCA - SOS modified & updated according to SOS, OPL given to all associates | Man | Rajesh Morkar | 2026-02-05 | Y
XUV3XO | X_FL_AC_3XO_Feb26_SJ_01 | 2026-02-07 |  | Trim 1 | Swaroop joshi | At AC leak test stage- protective cover not used by stage person | RC- associate not followed the SOS ICA - Awareness given to associate through DRF PCA - Alternator protective cover made available in case of misplace / not found | Man | Tushar Kulkarni | 2026-02-08 | Y
THAR ROXX | S_EP_RAD_RX_Nov25_RM_06 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Pokayoke machine Leak rate to be audited | Verification – 1.Testing pressure – 5.5 Bar Allowable leak – 0.5 Bar in 10 Sec 2. If inline pressure drop below 5bar will trigger alert & Pokayoke stop working Audits – ATOC pokayoke is already part of daily MQA pokayoke audit & MQA traveller Card audit | Machine | Rajesh Morkar | 2025-11-01 | Y
THAR ROXX | S_EP_RAD_RX_Nov25_RM_07 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Additional “press” point at grill fitment to be started | Action – Additional “Press” point at AC pipe fitment started with confirmation marking Sustenance – AC pipe fitment SOP is revised | Method | Rajesh Morkar | 2025-11-19 | G
THAR ROXX | S_EP_RAD_RX_Nov25_RM_08 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Z stage Key point to be display at stage | Action - DRF format displayed at stage | Man | Rajesh Morkar | 2025-11-14 | G
THAR ROXX | S_T1_CCB_RX_Jan26_SJ_01 | 2026-01-29 |  | CCB Stage | Swaroop Joshi | CCB to HVAC wiring clipping not done | Root cause: Stage associate forget to do the clipping Initial Analysis:- Associate forget to do the clipping. Also, few vehicles are observed with wiring harness clip mismatch / clip orientation wrong. Immediate Action: DRF given to all stage associates. All WIP vehicles checked and found be ok. Action : Check point is added to next station at CCB fitment to BIW Re-litmus test taken by SMT | Man | Rajesh Morkar | 2026-01-31 | Y
XUV3XO | X_T1_AF_3XO_Jan26_SJ_01 | 2026-01-21 |  | Trim 1 | Swaroop joshi | Antenna fitment process was not followed, as the operator did not hold the antenna from the top and instead directly tightened it from inside the vehicle. | RC- associate not followed the SOS ICA - Awareness given to associate through DRF PCA - Process correction done in such a way that antenna tightening associate will not tighten the antenna until it will be hold by another associate | Man | Dinesh Thakare | 2026-01-23 | Y
THAR ROXX | S_T1_CCB_RX_Dec25_SJ_01 | 2025-12-08 |  | CCB Stage | Swaroop Joshi | IP wiring clipping not done resulting ,IP wiring fouling with the sharp bottom edge of the edge of the CCB bracket | Root cause: Stage associate forget to do the clipping Initial Analysis:- Associate forget to do the clipping. Also, few vehicles are observed with wiring harness clip mismatch / clip orientation wrong. Immediate Action: DRF given to all stage associates. All WIP vehicles checked and found be ok. Action : Visually Checking started at buy-off | Man | Rajesh Morkar | 2025-12-09 | Y
XUV3XO | X_T1_LAT_3XO_Dec25_SJ_01 | 2025-12-22 |  | Trim 1 - latch | Swaroop Joshi | Tailgate switch fixture not used | RC- associate not followed the SOS ICA/PCA- Awareness given to associate through DRF | Man | Tushar Kulkarni | 2025-12-22 | Y
THAR ROXX | S_T2_IP_RX_Oct25_SR_01 | 2025-10-15 |  | IP topper Pad | Samir Rawte | During fitment of IP topper Pad (AC Vent) – Hammering done to fix the part. Check AC vent clearance wrt fixture. | Blue mapping done on both Side topper pad with hammering fixture. Found ok. Sufficient gap observed between fixture & vent | Method | Meenesh Patil | 2025-10-16 | G
THAR ROXX | S_T1_Latch_RX_Oct25_SR_02 | 2025-10-15 |  | Latch | Samir Rawte | Tail gate latch & Dove tail distance benchmarking to be done with Wrangler & compare spare wheel mounting position | Tailgate dove tail position of Wrangler & THAR is same. Wrangler customer are also experiencing same issue Local & Global market. Some quick fix after market solution available but it could not solve issue 100% | Material | Ajinkya Jadhav | 2025-10-16 | Y
THAR ROXX | S_CS_NOX_RX_Oct25_SR_03 | 2025-10-15 |  | NOX Sensor | Samir Rawte | Residual torque data to be confirmed | Torque conformity verified - Tool audit last 6 months data - Cp - 6.19, Cpk - 5.74 Residual Torque data - Cp - 6.74, Cpk - 6.35 | Machine | Vikrant Ghule | 2025-10-16 | G
THAR ROXX | S_CS_NOX_RX_Oct25_SR_04 | 2025-10-15 |  | NOX Sensor | Samir Rawte | Torque wrench daily report / calibration frequency to be confirm | Torque Wrench conformity verified - Frequency - Daily Cp - 10.95, Cpk - 10.58 Torque Wrech Calibration Frequency - 1/6 months Last 3 Calibration Record - 17.09.25, 17.03.25, 16.09.24 | Machine | Vikrant Ghule | 2025-10-16 | G
XUV3XO | X_FL_DS_3XO_Oct25_SJ_01 | 2025-10-15 |  | Door Setting | Swaroop Joshi | Tail gate Striker fixture not used | RC- Tailgate striker fixture not used as new associate deployed on stage. ICA -Awareness given to all stage associates PCA - Commitment letter taken from associate. | Man | Priyanka Jadhav | 2025-10-05 | G
THAR ROXX | S_CS_STAB_RX_Sep25_SR_01 | 2025-09-01 |  | ECU Flashing | Mukesh Deo | ESD noncompliance ECU stage – The operator not using apron ECU stage – Operator has not pulled the chain for ESD discharge while entering the workstation | RC1 - Chain location is at extreme end of door RC2 - Associate Negligence PCA - Nos of Static discharge chain increased at entry gate to avoid associate error | Method | Rajesh Morkar | 2025-09-05 | G
XUV3XO | X_UB_ABS_3XO_Sep25_AS_01 | 2025-09-11 |  | ABS sub assy | Assan Saran | LHS ABS block poka yoke inoperative | Shutter not opening RC-Shutter linkage broken ICA - WIP checked, awareness given PCA - Shutter repaired | Machine | Ravi | 2025-09-30 | G
THAR ROXX | S_T2_SF_RX_Aug25_MD_01 | 2025-08-01 |  | Windshield Fitment | Mukesh Deo | Water leakage due to flip seal issue | Flip seal deletion | Material | Swaroop Joshi | 2025-09-01 | G
XUV3XO | X_NL_FL_3XO_Aug25_CD_01 | 2025-08-11 |  | Fuel lid fitment | C. Dhande | Fuel lid housing not lock | RC - Associate not pressed the complete pheriphery ICA- Awareness given to stage associate to press properly after fitment PCA- Checkpoint added at Buyoff for proper fitment | Man | Rohit | 2025-08-14 | G
THAR ROXX | S_T2_SF_RX_Jul25_MD_01 | 2025-07-30 |  | Speaker fitment | Mukesh Deo | Multiple Speaker staking & handling not ok | New storage trolley made & implemented online | Method | Pankaj Suryawanshi | 2025-07-31 | G
XUV3XO | X_T3_SW_3XO_Jul25_SJ_01 | 2025-07-23 |  | Spare wheel fitment | Swaroop Joshi | Spare wheel grommet poor fit | RC - Paint shop issue melt sheel on hole ICA/PCA - Awareness given to associate through DRF at paint shop. | Man | Sagar Thoke | 2025-07-25 | G
XUV3XO | X_T2_OF_3XO_Jul25_MD_02 | 2025-07-30 |  | ORVM fitment | Mukesh Deo | Power ORVM is folded manually which may lead to mechanism failure | External electrical supply provided at stage itself to fold ORVM electrically and hence avoided to failure due to this reason | Method | Rahul D. | 2025-08-28 | G
THAR ROXX | S_EP_VCF_RX_Jun25_RM_01 | 2025-06-08 |  | Exhaust V Clamp | Ravindra Matodkar | Possibility of Gasket tilting upward to be control while lug pressing | Mobile based Vision system to be implemented | Method | Sandip Joshi / Ajinkya Jadhav | 2025-06-15 | Y
XUV3XO | X_UB_SF_3XO_Jun25_AS_01 | 2025-06-04 |  | Speaker fitment | Assan Saran | Butyl sealant was not pressed and no bond with panel after water shield fitment. | RC - Associate not pressed the complete pheriphery of sealer specifically near latch area. ICA- Awareness given to stage associate to press properly after fitment PCA- Checkpoint added at Buyoff for proper fitment | Man | Nayan K | 2025-06-04 | G
XUV3XO | X_T2_SF_3XO_Jun25_SJ_02 | 2025-06-14 |  | Sunroof Fitment | Swaroop Joshi | Use of Roller,Spatula is not mentioned in Slandered operation sheet | RC - Spatula not recommended by R&D or CME - Not given in POS sheet ICA- PCA-NA | Method | Avinash M | 2025-06-14 | G
THAR ROXX | S_EP_VCF_RX_May25_RM_01 | 2025-05-08 |  | Exhaust V Clamp | Ravindra Matodkar | Possibility of Gasket tilting upward to be control while lug pressing | Mobile based Vision system to be implemented | Method | Sandip Joshi / Ajinkya Jadhav | 2025-06-15 | Y
THAR ROXX | S_EP_VCF_RX_May25_RM_02 | 2025-05-08 |  | Exhaust V Clamp | Ravindra Matodkar | Locating stud to be provided on engine bracket instead of inserting pin after EATS mounting | Locating stud on bracket - 5 engine made - trial failed due to SDPF not able to fit since stud restricting movement of SDPF in X direction | Material | Hemant Barde / Onkar Tolbande / Gajanan Shekokar | - | G
THAR ROXX | S_EP_VCF_RX_May25_RM_03 | 2025-05-08 |  | Exhaust V Clamp | Ravindra Matodkar | Flat resting face on cylinder head to be provided similar to XUV700 EATS mounting | Cylinder head flat resting face to be explore | Material | Hemant Barde / Onkar Tolbande / Gajanan Shekokar | TBD | Y
THAR ROXX | S_EP_VCF_RX_May25_RM_04 | 2025-05-08 |  | Exhaust V Clamp | Ravindra Matodkar | Improve bottom side compression ratio | Single piece V clamp to be implemented under deviation & trial for 1 month production | Material | Hemant Barde / Onkar Tolbande / Gajanan Shekokar | 2025-05-30 | Y
THAR ROXX | S_YS_SHR_RX_May25_SR_04 | 2025-05-27 |  | Shower Test | Samir Rawte | Frequent breakdowns of the yard audit shower test facility, combined with increased production volume, are making it difficult to comply with the product audit control plan | New Shower test facility implementation started | Method | Swaroop Joshi | 2026-03-31 | R
THAR ROXX | S_YS_ML_RX_May25_SR_05 | 2025-05-27 |  | ML | Samir Rawte | Due to constraints in yard design and handling capacity at Nashik plant, contributing to high ML & DDS issue in dealership PDI Receipt | Yard re-layouting feasibility to be studied | Method | Assan Saran | TBD | R
XUV3XO | X_T2_CF_3XO_May25_CD_01 | 2025-05-30 |  | Cockpit flashing stage | C Dhande | Teflon block used for cockpit flashing is wear out | Teflon block changed | Machine | Rahul D | 2025-05-30 | G
XUV3XO | X_T2_AC_3XO_May25_SJ_02 | 2025-05-31 |  | AC pipe Fitment | Swaroop Joshi | HVAC unit drain hose not properly routed. | ICA- Awareness given to stage associate as OPL displayed online commitment later taken from asscoaite. PCA- Velcro on the Dash Mat feasibility to be checked | Material | Atul Kale | 2025-06-30 | G
XUV3XO | X_EP_VC_3XO_May25_SJ_03 | 2025-05-31 |  | Exhuast V clamp | Swaroop Joshi | Exhuast clamp tightening marking not done | ICA- Awareness given to stage associate as OPL displayed online commitment later taken from asscoaite. | Man | Rahul D | 2025-05-31 | G
THAR ROXX | S_T2_RAF_RX_Apr25_SJ_01 | 2025-04-15 |  | Rear Applique | Swaroop Joshi | Rear applique bracket loose | Rr applique bkt & RR applique fitment stage separation | Method | Sakharam Shelke | 2025-04-30 | Y
THAR ROXX | S_CAI_S&R_RX_Apr25_SR_02 | 2025-04-15 |  | S&R test | Samir Rawte | The detection of BSR (Buzz, Squeak, and Rattle) issues on the test track is currently unfeasible due to the absence of necessary infrastructure | Modification in current BSR track started | Method | Swaroop Joshi | 2026-03-31 | R
THAR ROXX | S_CAI_TL_RX_Apr25_SR_03 | 2025-04-15 |  | S&R test | Samir Rawte | Scorpio and THAR TCF lines are currently not D2D ready due to the unavailability of the D2D conveyor | D2D conveyor feasibility to be study | Method | Assan Saran | FY26H1 | R
XUV3XO | X_T1_SF_3XO_Apr25_SJ_01 | 2025-04-25 |  | Sunroof fitment | Swaroop Joshi | Single pan Sun roof – manipulator not used | ICA- Awareness given to stage associate PCA- Equipment PM frequnecy changed | Machine | Ravi D | 2025-04-25 | G
XUV3XO | X_T2_WG_3XO_Apr25_AS_02 | 2025-04-15 |  | Window glass fitment | Assan Saran | Power windoww not working- wire getting pinched during assembly- Routing error- clip missing | ICA- WIP checked no abnormility found Awareness given to stage associate and buyoff person PCA- Stock part checked at incomming | Man | Avinash M | 2025-04-15 | G
XUV3XO |  | 2024-08-20 |  | AC Pipe | Swaroop Joshi / Mukesh Deo / C Dhande | Double O-ring for AC joints for 100% (Upper body) | EN - S220-EN-A003-000192 raised in sytem Condenser joint implementation by 30-Nov-25 | Material | Atul Kale | Dec'25 | Y
THAR ROXX | Design Improvement - 1 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Comparison of Spout on both sides | As per M&M drawing Spout width ok, but as per Norma requirement & Standard SAE J2044 not ok | Material | Girish Banghale | TBD | R
THAR ROXX | Design Improvement - 2 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Reconfirmation with M/s NORMA for all parameters for temperature considering joints variation in plastic to metal connection | As confirmed by COE Mr. Girish -Supplier did Connector validation along with Machine spout as per SAE standard spout and we are using non machine spout. | Material | Girish Banghale | TBD | R
THAR ROXX | Design Improvement - 3 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | SOR document to be given to M/s NORMA to be checked | SOR not submitted by COE | Material | Girish Banghale | TBD | R
THAR ROXX | Design Improvement - 4 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Review & revisit vehicle level vibration | As per M&M drawing Spout width ok, but as per Norma requirement & Standard SAE J2044 not ok | Material | Girish Banghale | TBD | R
THAR ROXX | Design Improvement - 5 | 2025-11-14 |  | Radiator Fitment | 1. Ravindra Motodkar 2. Mukesh Deo 3. Samir Rawte | Bead of AOC to be check & study | As per M&M drawing Spout width ok, but as per Norma requirement & Standard SAE J2044 not ok | Material | Girish Banghale | TBD | R