## Sheet1
Sr.No | Concern ID | Concern | Type | Root Cause | Action Plan | Target Date | Closure Date | RYG | Attri. | Comm | Line | Stage No | Z/E | ATTRIBUTION | Part | Phenomena | Total Incidenes | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Field defect after cut off | Status (3 Month basis)
1 | XUV3XO_3 | Vehicle reported to us with complaint of Engine Crank but does not start- Replace Compartment Harness | WH | F22-Engine vibration & OBD Lamp ON:- Foreign particle trapped between injector and connector terminal F23-AMT TCU connector wiring rub with battery trey | 1.To avoid incorrect sequence fitment of connector, marking on wiring harness to be started -To avoid foreign particle inside injector connector area, check point and marking added at MHEPL 2.Cot tube added on AMT TCU branch | 2024-03-01 |  | G | Supplier Process | E&E | Trim 1 | T1-05 | Z | P | Compartment Wiring | Failure | 4 | 2025-04-01: 3; 2025-07-01: 1 | 0 | G